Timetable for Early Childhood Association

GST Manual

| Scheduled Date | Actual Date | Action |
| --- | --- | --- |
| 10 Jan |  | Designer to send draft out to 2 designers. First layout by 13 Jan |
| 13 Jan | 14 Jan | First Wingrove design to AP |
| 17 Jan | 18 Jan | Julia’s design to AP |
| 18 Jan | 18 Jan | Julia withdraws. |
|  | 19 Jan | Second Wingrove design to AP |
| 14 Jan |  | AP to choose which one to get the job |
| 19 Jan |  | Confirmation by AP |
| 24 Jan |  | Final text to designer so designer can start |
| 27 Jan |  | First draft layout completed |
| 31 Jan |  | AP to edit. |
| 31 Jan |  | Changes back to designer by noon same day. |
| 2 Feb |  | Draft layout to AP |
| 3 & 4 Feb |  | Last minute changes |
| 7 Feb |  | To printer |
| 21-24 Feb |  | Copies back from printer |

AP to be in Canberra for 2 weeks 24 January  - 7 February 2000.